## Carta Gantt
Carta Gantt
Nombre Proyecto: | LogisticFour
Nombre Participantes: | Freddy Cardenas,Kevin Bustos,Luis Mardones,Antonio Martinez,Mario Silva
Fecha: | 2025-07-18
Tarea | Tiempo
| Semana 1 | [6 empty] | Semana 2 | [6 empty] | Semana 3 | [6 empty] | Semana 4 | [6 empty] | Semana 5 | [6 empty] | Semana 6 | [6 empty] | Semana 6 | [6 empty] | Semana 7 | [6 empty] | Semana 8 | [6 empty] | Semana 9 | [6 empty] | Semana 10 | [6 empty] | Semana 11 | [6 empty] | Semana 12 | [6 empty] | Semana 13 | [6 empty] | Semana 14 | [6 empty] | Semana 15 | [6 empty] | Semana 16 | [6 empty] | Semana 17 | [6 empty] | Semana 18
| agosto | [24 empty] | Septiembre | [29 empty] | Octubre | [30 empty] | Noviembre | [29 empty] | Diciembre
Phase 1 - Project Definition | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Project Ideas (First Meeting)
Personal Documents
Group Documents
Meeting Minutes
Business Case and Work Plan
Mockups
Articles of Incorporation
WBS (Work Breakdown Structure)
WBS Matrix
Requirements Sheet
Gantt Chart
Use Case Diagram
Extended Use Case Document
ERS Documentation
Phase 1 Presentation | [32 empty] | Entrega
Phase 2 - Project Development
RACI Matrix
Risk Matrix
Meeting Minutes
Change Control Matrix
Business Process Document
Spring Preview Document
Data Dictionary
DAS (System Architecture Document)
Personal Documents
Group Documents | [54 empty] | Entrega
Web Page Development
Desktop Application Development
Phase 2 Presentation | [102 empty] | Entrega
Phase 3 - Project Presentation
Personal Documents
Group Documents
Scope Verification
Defect Log Sheet
Test Plan
Plan de Capacitacion
Matriz de Prueba BD
Matriz de Control de cambios
Manual de Usuario
Informe Cierre de Proyecto
Documento avance Spring
Presentacion Fase 3 | [116 empty] | Entrega
Leyenda
NOMBRE RECURSO | SIGLA | [6 empty] | ROL
Freddy Cardenas | JP | [6 empty] | Jefe de Proyecto
Kevin Bustos | APC | [6 empty] | Analista Programador
Antonio Martinez | DBA | [6 empty] | Administrador BD
Luis Mardones | QA | [6 empty] | Calidad Y Testing
Mario Silva | DG | [6 empty] | Diseñador
Más de un miembro del equipo | [7 empty] | Más de un rol
Dias no habiles | [7 empty] | N/A
Rango de entregas por fase | [7 empty] | N/A